## Blad1
File updated 2024-11-12
Activity | Time | Administration (on behalf of ÄR/director of studies) | Academy | Note. | Status
Inform the Dean, Chair ÄR, Director of Doctoral Studies, FUS and KOM that the public defence will take place | As early as possible |  | Main supervisor | Must be documented in the ISP
Based on the meeting dates of ÄR and FoUN, make a preliminary timetable for handling decisions | As early as possible |  | Director of Studies | The Research Committee (which will prepare the matter) meets 14 days before FoUN. Contact the board secretary well in advance.
Contact opponent | As early as possible |  | Main supervisor in collaboration with the ÄR and director of studies
ÄR prepares proposals for the opponent, grading committee and time | As early as possible |  | The director of studies is responsible for ensuring that the case is taken to ÄR and then on to FoUN.
Plan for proofreading | As early as possible |  | Doctoral student
Contact ALB/publication coordinator for scheduling of proofreading, printing and dissemination of the thesis. | At least 14 weeks in advance |  | Doctoral student
Determination of the opponent and the grading committee of FoUN | Latest 14 weeks in advance |  | The director of studies is responsible for ensuring that the matter is taken to FoUN | Please note that it is not allowed to pay members employed at FHS.
Determination of date by the Head of Research | At least 14 weeks in advance |  | FUS is responsible for ensuring that the matter is taken to the head of research | cc KOM
Booking of a venue for the public defence (e.g. Sverigesalen, Klassrum 2000, Leijonskiöldska) | At least 14 weeks in advance | Dept. Adm. |  | Preliminarily book both the venue for the public defence and for the reception a few possible dates before the date is set to ensure that the premises are available.
Booking of room for reception (Mässen?) | 14 weeks in advance | Dept. Adm. | ÄR via Dept. Adm. | I'm commenting on above.
Booking of a room for reception and refreshments with the grading committee. | 14 weeks in advance | Dept. Adm. |  | Each subject decides on the form of this
Book ”Spikning” with ALB | 14-6 weeks in advance |  | Doctoral student in collaboration with main supervisor | Must be done at least three weeks in advance
Standing invitations: Vice-Chancellor, Pro Vice-Chancellor, Deputy Vice-Chancellor, Dean, the student union? | 14-10 weeks in advance? | Dept. Adm. |  | Information
Invited according to the wishes of the doctoral student | 14-10 weeks in advance? |  | Doctoral student in collaboration with the Director of Studies
Create and send invitation with link to form (Templates are available at KOM) | 14-8 weeks in advance | Dept. Adm. |  | Ask the KOM about the time (or when the date and opponent are set?)
Book travel and hotel for opponents. | 8 weeks in advance | Dept. Adm. |  | SEK 35,000 per disser­­tation is allocated to the subject budget. Excess costs are handled by the department/subject. (Ö 784/2022)
Make a so-called SINK application if the opponent or participant in the examining committee is a foreign citizen | 8 weeks in advance | Inst Adm via HR Lön
Order from service (use the service portal): | 8 weeks in advance | Dept. Adm.
· extra cleaning of Sverigesalen, | 8 weeks in advance | Dept. Adm.
· decoration in Sverigesalen (tablecloth, Marieberg bell, candle holders) | 8 weeks in advance | Dept. Adm.
· Flags in the Sweden Hall | 8 weeks in advance | Dept. Adm.
· Flying the flag outdoors | 8 weeks in advance | Service or Protocol?
Order support from Helpdesk/IT (or ALB?) for Sverigesalen during the public defence (use the service portal): | 8 weeks in advance | Dept. Adm.
Info is posted in FHS's calendar MyFHS and on the External Web. | 8 weeks in advance? | KOM |  | Including open invitation
Estimate the number of participants at the reception (Invited according to the wishes of the doctoral student, the grading committee standing invited and a few extras) | 8 weeks in advance |  | The director of studies collects information and contacts the Dept Adm
Order catering and staff for reception, examination committee and reception in the mess, table water for Sverigsalen for doctoral student and opponent (made via purchase in Agresso for the catering company) | 8 weeks in advance | Dept. Adm. |  | Adjust the number of participants if necessary, about 1 week before the public defence. (NOTE! Sparkling wine must be ordered through the fair council if it is to be served in the mess hall).
C Org/E decision on serving alcohol | 8 weeks in advance | Dept. Adm. |  | Pursuant to Decision Ö 321/2015, point 3.3.3. is enough decision by C orgE.
Order drinks (sparkling wine incl non-alcoholic alternative) for the reception, examination committee and reception in Mäss (made via purchases in Agresso to Mässrådet). Staff from Mässrådet must also be on site and serve. | 8 weeks in advance | Dept. Adm.
Inform the guard about the public defence | 4 weeks in advance | Inst Adm
Check with the guard if extra guards are needed for the reception in the mess. In that case, make a requisition in Agresso. | 4 weeks in advance | Inst Adm
Book an appointment with KOM for news on the website and possibly a photo. | 4 weeks in advance? |  | Director of studies contacts KOM
Order flower decoration for Sverigesalen (made via purchase in Agresso) | 4 weeks in advance | Dept. Adm.
Order flowers for the doctoral student (made via purchase in Agresso) | 4 weeks in advance | Dept. Adm.
Possible digital transmission of the public defence document | 4 weeks in advance |  | Director of studies contacts ALB
Possible ceremony for ”spikning” | 3 weeks in advance |  | ÄR/Director of Studies
Copies of the thesis are sent to the opponent and the examining committee |  |  | Doctoral student
Inform the Protocol and the head of security if the opponent or someone on the grading committee is a foreign citizen. | 1 week in advance | Dept. Adm.
Registration for participants in the examining committee and opponent (if they will be staying in a room other than Sverigesalen and Leijonsköldska). | 1 week in advance | Dept. Adm.
Send out a link to digital participants | a few days before the date of the public defence |  | Director of Studies
Contact with the catering company and the Mässrådet before reception. Monitor the delivery of flowers. | Dissertation day | Inst Adm
Sign/Information in the stairwell/reception about the public defence | Dissertation day | Dept Adm and KOM?
Decorate the Sverigesalen, tablecloth, flowers, etc. Table water and notepad for respondent and opponent). Mark reserved seats for the examining committee etc. | Dissertation day | Inst Adm using Service
Ensure that the opponent and the grading committee receive a fee (and reimbursement for any travel expenses). Please note that it is not allowed to pay members employed at FHS. | After the public defence | Director of Studies via Dept. Adm. Gm HR Lön | Director of Studies via Dept. Adm. Gm HR Lön | Decision Ö 784/2022
Recommendation: The department/ÄR should appoint a person responsible for each public defence of the thesis to hold the event together